## Slide 1: ERECON Software Development
Project Management
Presented By
Hem Bahadur Gurung
Furnima Sherpa

## Slide 2: Introduction
It’s a web based accounting software-eRecon project of Physician Service Group for Hospital Corporation Of America with two year completion.

## Slide 3: Facts
Begin November 2012
3 SQL server purchase $ 6000
Deadline December 2014
Documenting requirement after oct 2013
Phase 1 completed June 6,2014
July28 2014 meeting
held
Reconciling November balance December 9,2014

## Slide 4: Problems
Issue on obtaining critical source data from HR
Lafferty and Ray who were project manager don't have any prior practical experience on software development project
Software developers were resistant to providing time estimates on tasks.
Corey and Mendoza who are having 10 years in data base project were uncomfortable on using Waterfall methodology.
Mayer restated on difficulty in accessing raw data due to incomplete in approval of CEO.

## Slide 5: Phases of projects
Phase 1:Global Approvals –
          Creation of Home page and global approvals page
          Accessible by directors and vice presidents
          Reconcile and review 12,000 to 35,000 general ledger accounts
          Low risk groups of account were identified.
          Reviewed existing accounts and added new low risk group of accounts
          Tested every month of each low risk accounts for global approval related with HCA accounting
          Global approval completed by VP,11th day of each month.GL account balances were final. No transaction occurs after.
Part 1

## Slide 6
    Phase 2: Reconciliation and Filter
            Top left user chose filter:
                Provide user flexibility to navigate to their assigned work by populating a list of CoID accounts-based o set parameters
            Top right filter results:
                Listed records containing the CoID number,
                account number and GL balance
            Bottom displayed the reconciliation;
                displayed detail of reconciliation,
                add reconciling items and to conduct,
                recon item include PE date,
                description amount and note field
Part 2

## Slide 7
Phase 3: Post Close Review Guide (PCRG)
  To replace existing reconciliation
  Based on Microsoft Access Application
  Recording completion and approval of reconciliation and reporting
  Users can prepare reconciliation and submit them to review and reviewers review and chose to approve or reject reconciliation.
  After all CoIDs in a division approve on screen, Managers were able to perform reviews at a division level on the monthly certification page.
Part 3

## Slide 8
Phase 4: Support Store
          Adding functionality to the reconciliation page,
          preparers to attach documents to reconciliations as supporting documentation.
Phase 5 Journal Entries
          To create a journal entry directly from reconciliation item line,
          entering the offsetting CoID and account.
Phase 6: Home page Enhancement
          Home page, created in phase 1 enhanced to include a dashboard
Part 4

## Slide 9: Phase 2 components
SQL Server Database
    Shared Database
      Contains Computer master, account balance, general ledger account list and journal entry trasnactions Table
      Source data (2 days),Optimal load (2 days)
      Load and validate data in development (2 days)
      After four data validation, pushed shared database to QA for Testing (5-6days)
      IT and S department responsible for Pushing to QA
      Mendoza assigned to validation
      After tested data base verified, pushed for production
      At July 28 team shared completion of database
Part 1

## Slide 10
Security Database
    Finalize table-naming conventions (one day)
    Mendoza merge existing security table (one day)
    Young needed to gather minimum technical requirements for security database (one day)
    Mendoza create the views and SPROCS necessary for eRecon to operate properly(3 days)
    Mendoza responsible for employee fact table and for the system or base tables.
    Mayer has to access data from HR within 10 to 15 days.
    After that, technical team is responsible for defining scope and business rules of the load. (4 to one week)

## Slide 11: Microsoft.NET
More appealing to users, sophisticated user experience than other platforms and gave more developers more flexibility in design.
User Interface completed by Young
Interface, account grouping, batch process, security and archive
Young is using Model View Controller(MVC) Model design pattern (8 to 12 days),Controller - web browser-model HTML and view SQL
Persist with data four days and complete client scripting (10 to 15 days)
young needed Accounting grouping section (10 to 12 days)
Part 1

## Slide 12: Microsoft.NET
Batch processing- Mendoza (10 days),Young Security section need an MVC(2 days) and coding the service and repository (3 to 5 days)
Unit testing(1.25 days),Archive table (one day),Modifying the SSIS package to copy or clear(one day)
The Push to QA Young submit work ticket to system group in IT and S (one day)
Ray needed to produce test plan and test scripts before the month longer acceptance testing.(1-2 weeks)
After Young submitted a work ticket the system group push to production.
Part 2

## Slide 13: Conclusion
Think strategically and Practically
Project duration should not be upturn due to Data Extraction
Software developers be hired based on skills on related subjects